## ChangeLOG
Project Change Log
Release # | Change Description | Date | Affected Page(s)
Iteration 1 | Original Release | 2021-03-12 | All
Iteration 2 | Original Release | 2021-04-09 | All
Iteration 3 | "Time Calculation" removed from project description and requirements, for clarification. | 2021-05-03 | 2.3,5
| Project Description updated with clarification on wireless resources, (also, new line numbers). | 2021-05-03 | 2,3
| Requirements updated to match project description. | 2021-05-03 | 5

## Requirements
Requirements
Req ID | Req Statement | Line (From Project Description)
R1 | The system shall provide for authenticated login to the ShareList app.
R1.1 | Register. | 41
R1.2 | Login.
R1.3 | Log Off.
R1.4 | Reset password.
R2 | The system shall provide group admins the ability to:
R2.1 | Add tasks. | 42,43
R2.2 | Remove tasks.
R2.3 | Edit tasks.
R2.4 | Assign tasks.
R2.5 | Add users to group. | 46,47
R2.6 | Remove users from the group. | 34,35
R2.7 | Add new group admins to group. | 18,47
R2.8 | Delete group | 48,49
R2.9 | Edit group. | 46,47
R3 | The system shall provide all users the ability to:
R3.1 | Mark task as completed. | 45
R3.2 | Create groups. | 46,47
R4 | The system shall provide the ability to search by keywords. | 44
R5 | The system shall provide tasks the ability to:
R5.1 | Be visible to all members in that group. | 22,23
R5.2 | Have users assigned to it. | 42,43
R5.3 | Have assigned users mark it as completed. | 45
R6 | The system shall provide tasks the following properties: start time, completion time, due date, time spent, title, description, users assigned | 26,27,28,29,30,31
R7 | The sytem shall provide users the ability to create groups, and have group admin status when they do. | 46,47
R8 | The system shall provide a database used for storing information related to tasks, groups, users. | 57
R9 | The system shall provide wireless resources used for syncing between each user's device and the database in realtime. | 58,59
R10 | The system shall provide a group summary function, which will accomplish: | 50
R10.1 | Calculating and reporting the tasks completed. | 52
R10.2 | Calculating and reporting the in-progress tasks. | 53
R10.3 | Calculating and reporting the remaining tasks. | 54

## Use Case List
Use Case List
Use Case # | Use Case Name
UC1 | Login
UC1.1 | Register.
UC1.2 | Login.
UC1.3 | Log Off.
UC1.4 | Reset password.
UC2 | Manage task
UC2.1 | Add tasks.
UC2.2 | Remove tasks.
UC2.3 | Edit tasks.
UC2.4 | Assign tasks.
UC3 | Manage group
UC3.1 | Add users.
UC3.2 | Remove users.
UC3.3 | Add admins.
UC3.4 | Delete groups
UC3.5 | Edit groups.
UC4 | Mark task as completed
UC5 | Create groups.
UC6 | Search by keywords.
UC7 | Generate summary

## RUCTM
RUCTM
Req ID | Priority Weight | UC 1 | UC 1.1 | UC 1.2 | UC 1.3 | UC 1.4 | UC 2 | UC 2.1 | UC 2.2 | UC 2.3 | UC 2.4 | UC 3 | UC 3.1 | UC 3.2 | UC 3.3 | UC 3.4 | UC 3.5 | UC 4 | UC 5 | UC 6 | UC 7
R1 | 3 | X
R1.1 |  |  | X
R1.2 |  |  |  | X
R1.3 |  |  |  |  | X
R1.4 | [5 empty] | X
R2 | 1 | [5 empty] | X
R2.1 | [7 empty] | X
R2.2 | [8 empty] | X
R2.3 | [9 empty] | X
R2.4 | [10 empty] | X
R2.5 | [12 empty] | X
R2.6 | [13 empty] | X
R2.7 | [14 empty] | X
R2.8 | [15 empty] | X
R2.9 | [16 empty] | X
R3
R3.1 | [17 empty] | X
R3.2 | [18 empty] | X
R4 | 6 | [18 empty] | X
R5 | 1 | [5 empty] | X
R5.1 | [7 empty] | X
R5.2 | [8 empty] | X
R5.3 | [9 empty] | X
R6
R7 | 1 | [10 empty] | X
R8 | 2
R9 | 4
R10 | 5 | [19 empty] | X
R10.1 | [20 empty] | X
R10.2 | [20 empty] | X
R10.3 | [20 empty] | X
Score |  | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 24
Legend: | 1 is highest priority. Work 1 First.
10

## Increment Matrix
Increment Matrix
Use Case # | Priority | Effort (Person-weeks) | Depends on | Iteration 1 (03/12) | Iteration 2 (04/09) | Iteration 3 (05/03)
UC1 | 3 |  | None
UC1.1 |  | 6 |  |  | 6
UC1.2 |  | 6 |  |  | 6
UC1.3 |  | 6 |  |  | 6
UC1.4 |  | 6 |  |  |  | 6
UC2 | 2 |  | None
UC2.1 |  | 2 |  | 2
UC2.2 |  | 2 |  |  |  | 2
UC2.3 |  | 2 |  |  | 2
UC2.4 | 1 | 3 |  |  | 3
UC3 |  |  | UC 1
UC3.1 |  | 4 |  |  | 4
UC3.2 |  | 4 |  |  | 4
UC3.3 |  | 4 |  |  |  | 4
UC3.4 |  | 4 |  |  |  | 4
UC3.5 |  | 4 |  |  |  | 4
UC4 |  | 3 | UC 2 |  | 3
UC5 |  | 4 | UC 3 |  | 4
UC6 | 5 | 2 | UC 2 |  | 2
UC7 | 4 | 1 |  |  |  | 2
Total Effort |  | 63 |  | 2 | 40 | 22
1 PW = 5 hrs |  |  |  | 10 | 200 | 110

## Task List
Task List
Assigned to... | Iteration 2 | Iteration 3 | Use Case
Mohammed & Anum | Add tasks. |  | 2.1
|  | Remove tasks. | 2.2
Yanzhi & Yu | Register. |  | 1.1
| Login. |  | 1.2
Mohammed & Anum | Manage task. |  | 2
| Edit tasks. |  | 2.3
Hannan | Mark task as completed. |  | 4
| Create groups. |  | 5
| Search by keywords. |  | 6
|  | Generate summary. | 7
Yanzhi & Yu | Log Off. |  | 1.3
|  | Reset password. | 1.4
Mohammed & Anum | Assign tasks. |  | 2.4
| Manage group. |  | 3
| Add users. |  | 3.1
| Remove users. |  | 3.2
|  | Add admins. | 3.3
|  | Delete groups. | 3.4
|  | Edit groups. | 3.5